RESONATE CLUB INC.
리조네이트 클럽 주식회사

Premium Korea↔USA Travel | Business Proposal

Date: June 11, 2026
Investor: U.S. Citizen/Entity (100% Equity)
CEO: Hee Sung Lee (F-4 Visa)
Brand: Resonate Tour (결 투어)

# 1. Executive Summary

Resonate Club Inc. is a premium travel planning corporation to be established in Haeundae-gu, Busan, Republic of Korea, under the Foreign Investment Promotion Act (FIPA). Operating under the brand 'Resonate Tour (결 투어),' the company specializes in all-inclusive, small-group premium golf tours from Korea to California.

The company will be registered as a Domestic & International Travel Agency with Planned Travel Operator status (국내외여행업 / 기획여행사), with a total paid-in capital of KRW 100,000,000 (~USD $74,100), fully funded by a U.S. investor holding 100% equity. Hee Sung Lee, an F-4 Overseas Korean Visa holder, will serve as non-shareholder Representative Director (CEO).

Key financials: Monthly fixed costs of KRW 1,727,000, guarantee insurance of KRW 230,000,000 (Base KRW 30,000,000 + Planned Travel KRW 200,000,000), and a cost-plus-40% markup model targeting 12–18 premium golf tour groups in Year 1.

# 2. Company Overview

| Item | Detail |
| --- | --- |
| Legal Entity | Resonate Club Inc. — Foreign-Invested Joint-Stock Company (주식회사) |
| Brand | Resonate Tour (결 투어) |
| Business Type | Domestic & International Travel Agency — Planned Travel Operator |
| Registered Office | Haeundae-gu, Busan, Republic of Korea |
| Paid-in Capital | KRW 100,000,000 (statutory minimum KRW 50,000,000) |
| Shares | 2,000 common shares at KRW 50,000/share |
| Ownership | U.S. Investor: 100% (sole shareholder) |
| CEO | Hee Sung Lee — F-4 Visa, non-shareholder Representative Director (salaried) |
| Planned Establishment | August 2026 — Operations from late September 2026 |
| Web | resonatetour.com / resonateclub.com |

# 3. Business Model & Services

## 3.1 Primary Service: Korea→USA Premium Golf Tours

Target: High-net-worth Korean golfers (annual income KRW 100M+, ages 35–60)
Operating model: Small private groups (2–8 persons), all-inclusive, fully customized
Pricing: Cost + 40% transparent markup (cost never disclosed to clients)
Included: Round-trip flights, 5-star hotels, premium golf courses, private van + driver, Korean-speaking guide, all meals, cinematic trip reel

| Package | Duration | Rounds | Price (USD/person) | Key Courses |
| --- | --- | --- | --- | --- |
| Trump Premier | 6N/7D | 4 rounds | $9,752 | Trump National LA, Sandpiper GC, Hidden Valley GC, The Crossings |
| Trump Elite | 5N/6D | 3 rounds | $7,741 | Trump National LA, Sandpiper GC, Hidden Valley GC |

## 3.2 Future Expansion: USA→Korea Inbound Luxury Tours

After upgrading to a Comprehensive Travel Agency (종합여행업) license, the company will expand to serve American luxury travelers visiting Korea for K-culture, premium golf, and Michelin dining experiences.

| Package | Duration | Price (USD/person) | Highlights |
| --- | --- | --- | --- |
| Korea Golf Premier | 11N/12D | $27,300 | Nine Bridges, South Cape, Jack Nicklaus GC |
| Korea Discovery | 12N/13D | $27,580 | K-Culture + Golf + Michelin Dining |

## 3.3 VIP Events

Curated, ultra-exclusive events such as the Moving Day VVIP Invitational (8 guests only, $14,400/person) hosted by Aimee Cho, offering access and experiences unavailable through mass-market channels.

# 4. Corporate Structure & Governance

| Role | Person | Status | Key Responsibilities |
| --- | --- | --- | --- |
| Sole Shareholder (100%) | U.S. Investor | D-8-1 Corporate Investment Visa | Capital provision, strategic oversight, board-level decisions |
| Representative Director (CEO) | Hee Sung Lee | F-4 Overseas Korean Visa Non-shareholder, salaried | Day-to-day operations, licensing, banking, contracts, tax filings, government relations |
| Director / Auditor | U.S. Investor | Registered on corporate registry | Legal compliance, major transaction approval |
| U.S. Partner (Vendor Manager) | TBD | Based in California | Local vendor management, course scouting, on-site tour operations, content creation |

The CEO operates under a comprehensive Power of Attorney from the investor, enabling full autonomy for daily operations. Major decisions (capital changes, M&A, dividend declarations) require board resolution with investor approval.

# 5. Establishment Timeline

| Phase | Dates | Key Actions | Outcome |
| --- | --- | --- | --- |
| Pre-Setup | Now – Jul 16 | Shareholder agreement, investor docs, engage Korean professionals | Ready for CEO arrival |
| STEP 1 | Jul 17–20 | CEO arrival Korea (F-4), Haeundae-gu office lease | Office secured |
| STEP 2 | Jul 21–23 | Articles of Incorporation + notarization | Notarized Articles |
| STEP 3 | Jul 24–30 | FDI notification → Capital deposit (KRW 100M) | FDI registration + bank certificate |
| STEP 4 | Jul 31 – Aug 6 | Corporation registration at Busan District Court | Legal entity established |
| STEP 5 | Aug 7–11 | Business registration at Haeundae Tax Office | Tax ID + business certificate |
| STEP 6 | Aug 12 – Sep 10 | Travel Agency License application (Haeundae-gu Office) | Domestic & Int'l Travel Agency License |
| STEP 7 | Aug 12 – Sep 17 | Guarantee Insurance (SGI) — KRW 230,000,000 + Liability Insurance | Full insurance compliance |
| STEP 8 | Sep 15 onward | Investor D-8 visa application (US Embassy) | Investor residency secured |
| Operations | Late Sep 2026 | First tour group departure | Revenue generation begins |

# 6. Financial Plan

## 6.1 Capital & Initial Costs

| Category | Amount (KRW) | USD (~1,350 rate) | Note |
| --- | --- | --- | --- |
| Paid-in Capital | 100,000,000 | $74,100 | Exceeds statutory minimum (KRW 50,000,000) |
| Initial Setup (registration, notary, office deposit) | ~5,000,000 | ~$3,700 | One-time costs |
| 1-Year Operating Reserve | ~25,000,000 | ~$18,500 | Monthly fixed × 12 + contingency |
| TOTAL Recommended | 130,000,000 | ~$96,300 | Covers first year of operations |

## 6.2 Monthly Fixed Costs

| Item | Monthly (KRW) | Annual (KRW) | Note |
| --- | --- | --- | --- |
| Office Rent (Haeundae-gu) | 800,000 | 9,600,000 | Small office, premium location |
| Guarantee Insurance (SGI) | 192,000 | 2,300,000 | Base 30,000,000 + Planned Travel 200,000,000 = 230,000,000 bond; ~1% premium |
| Liability Insurance | 35,000 | 420,000 | Mandatory under Tourism Promotion Act |
| Accounting & Tax Services | 300,000 | 3,600,000 | Monthly bookkeeping + annual tax filing |
| Telecom & Office Supplies | 200,000 | 2,400,000 | Internet, phone, sundries |
| Miscellaneous | 200,000 | 2,400,000 | Bank fees, memberships, contingency |
| Monthly Total | 1,727,000 | 20,724,000 |  |

## 6.3 Revenue Model

Core model: Cost-Plus 40% Markup

Year 1 Conservative Target (Sep 2026 – Aug 2027):
• 12–18 tour groups × avg 4 persons × ~$2,500 profit/person
• Gross profit: ~$120,000–180,000
• After operating costs: ~KRW 130M–200M (~$96K–148K) net profit

Year 2 (full calendar, 24+ groups): ~KRW 300M+ (~$222K+) net profit

Profit repatriation via dividends (10–15% Korean withholding, creditable against U.S. tax via Form 1116).

## 6.4 Guarantee Insurance Breakdown

As a Planned Travel Operator (기획여행사), the company must carry guarantee insurance protecting customer prepayments. The Tourism Promotion Act Enforcement Rules Schedule 3 require:
  • Base bond (국내외여행업): KRW 30,000,000
  • Planned Travel surcharge (기획여행 추가): KRW 200,000,000
  • TOTAL: KRW 230,000,000

This is an insurance PREMIUM (annual ~KRW 2.3M at ~1% rate), not a deposit. Additionally, mandatory Liability Insurance (배상책임보험) covers bodily/property damage during tours.

# 7. Licensing & Regulatory Compliance

| License/Permit | Legal Basis | Authority | Est. Duration |
| --- | --- | --- | --- |
| Corporation Registration | Commercial Act | Busan District Court (East) | 5–7 days |
| Business Registration | VAT Act | Haeundae Tax Office | 3–5 days |
| Travel Agency License | Tourism Promotion Act Art. 4 | Haeundae-gu Office | 2–4 weeks |
| Guarantee Insurance (SGI) | Tourism Act Enforcement Rules Sch. 3 | Seoul Guarantee Insurance | 5–7 days |
| Liability Insurance | Tourism Promotion Act | Private insurer | 3–5 days |
| FDI Registration | FIPA | KOTRA / Foreign Exchange Bank | 1–2 days |
| Tour Escort Registration | Tourism Promotion Act Art. 38 | Korea Tourism Organization | Hire qualified |

# 8. Investor Visa & Tax Benefits

## 8.1 D-8-1 Corporate Investment Visa

| Benefit | Details |
| --- | --- |
| Visa Type | D-8-1 (Corporate Investment) |
| Validity | 2–3 years initially, renewable up to 5 years, renewable indefinitely |
| Family | Spouse + minor children eligible for F-3 dependent visas |
| Healthcare | Full NHIS (National Health Insurance) coverage |
| PR Pathway | F-5 Permanent Residency: KRW 300M (~$200K) investment OR 2+ full-time Korean employees |

## 8.2 FIPA Tax Incentives

| Incentive | Benefit | Duration |
| --- | --- | --- |
| Corporate Income Tax Reduction | 100% exemption years 1–5, 50% years 6–7 | 7 years |
| Acquisition Tax Exemption | 100% on real estate, vehicles, equipment | 15 years |
| Property Tax Reduction | 100% years 1–5, 50% years 6–15 | 15 years |
| Customs Duty Exemption | 100% on imported capital goods | Within 3 years of FDI |
| Dividend Withholding (US-Korea Treaty) | 15% standard / 10% if held via corporate entity with ≥10% ownership | Ongoing |

# 9. Team & Key Partners

U.S. INVESTOR (100% Shareholder): Provides capital, strategic direction, and board-level oversight. Holds D-8-1 visa for Korean residency. Engages U.S. cross-border CPA for Form 5471, FBAR, and FATCA compliance.

HEE SUNG LEE (CEO, F-4 Visa): 20+ years U.S. residency, hands-on golf industry experience at American Golf Inc. / Recreation Park 18 Golf Course, extensive California/Hawaii course network, bilingual Korean-English. Manages all Korean operations: licensing, banking, tax, marketing, client relationships.

U.S. PARTNER (California-Based Vendor Manager): Manages all local vendors — golf courses, hotels, transport, restaurants. Scouts new courses, negotiates contracts, handles real-time tour operations, creates social media content. Revenue share: 20–30% of net profit per tour.

KOREAN CERTIFIED TAX ACCOUNTANT (세무사): Corporate tax filing, VAT returns, FIPA incentive applications, withholding tax on dividends. KRW 300,000–500,000/month.

U.S. CROSS-BORDER CPA: Form 5471 (foreign corporation reporting), FBAR, Form 1116 (foreign tax credit), Form 8938 (FATCA), PFIC analysis. $2,500–5,000 initial / $1,500–3,000/year.

# 10. Investment Case

Why invest in Resonate Club Inc.?

1. STRUCTURAL MARKET GROWTH: Korean golf population 6.24M, overseas golf travel growing at 12.5% CAGR. U.S. is the #2 destination for Korean outbound golf.

2. PREMIUM NICHE: Large agencies serve mass market; nobody owns the premium, customized, small-group California golf segment for Korean high-net-worth individuals.

3. UNFAIR ADVANTAGE: CEO's 20+ years U.S. golf industry experience, direct course relationships, bilingual/bicultural capability — impossible for Korean-only competitors to replicate.

4. CAPITAL-EFFICIENT: Low fixed cost base (KRW 1.73M/month), asset-light model, 40% markup provides predictable margins. Breakeven at ~5 tour groups per year.

5. SCALABLE: Model expands to USA→Korea inbound (K-culture) and VIP events without proportional cost increase.

6. TAX-ADVANTAGED: FIPA corporate tax holiday (years 1–5), customs duty exemption on vehicles and equipment, US-Korea tax treaty reduces dividend withholding.

7. CLEAN GOVERNANCE: 100% investor ownership, professional CEO, transparent cost-plus pricing, single-class share structure.

# 11. Risk Factors

| Risk | Level | Mitigation |
| --- | --- | --- |
| Regulatory change (capital increase) | Medium | Investor-backed capital exceeds requirements; legal counsel retained |
| SGI insurance denial | Medium | Strong business plan; Korea Credit Guarantee Fund backup route |
| D-8 visa delay | Low | Early application; 5–10 business days typical processing |
| FX fluctuation (KRW/USD) | Low | Revenue in USD, costs split — natural hedge |
| Slow Season 1 adoption | Medium | Conservative targets; 5 groups = breakeven |
| US tax compliance penalties | High | Cross-border CPA engaged pre-investment; Form 5471 filed annually |
| PFIC classification | Low | Active operating business; CPA opinion letter secured |

---
This business proposal synthesizes the latest corporate establishment plans as of June 11, 2026. All figures are based on the Tourism Promotion Act and its Enforcement Rules as currently in effect.