RESONATE CLUB INC.
CEO Action Plan — F-4 Visa Holder

Arrival July 17, 2026 — Step-by-Step Execution Timeline

Date: June 11, 2026
CEO: Hee Sung Lee (F-4 Overseas Korean Visa)
Investor: U.S. Investor (D-8-1, 90% Equity Stake)

# Overview

This document is a step-by-step execution manual for CEO Hee Sung Lee, arriving in Korea on July 17, 2026 on an F-4 Overseas Korean Visa. It covers every action required to establish the corporation by August 1 and complete all travel agency licensing by September.

Key Parameters:
• Investor: U.S. citizen/entity contributing KRW 90,000,000 (90% equity), D-8-1 visa
• CEO: Hee Sung Lee, F-4 visa, contributing KRW 10,000,000 (10% equity)
• Entity: Foreign-Invested Joint-Stock Company under FIPA
• Business: Domestic & International Travel Agency (Planned Travel Operator)
• Location: Haeundae-gu, Busan, Republic of Korea
• Capital: KRW 100,000,000 total (exceeds statutory minimum of KRW 50,000,000)
• Guarantee Insurance: KRW 230,000,000 (Base KRW 30,000,000 + Planned Travel KRW 200,000,000)
• Monthly Fixed Costs: KRW 1,727,000 (incl. insurance KRW 192,000 + liability KRW 35,000)
• Goal: Corporation registered by Aug 6, travel license by Sep 10, operations begin late September

# Master Timeline Summary

| Step | Est. Duration | Cumulative | Target Date |
| --- | --- | --- | --- |
| Pre-Arrival Prep (US) | Complete before arrival | D-14 | By Jul 3 |
| STEP 1: Office Lease | 1–3 days | D+3 | Jul 20 |
| STEP 2: Articles of Incorporation + Notarization | 2–3 days | D+6 | Jul 23 |
| STEP 3: FDI Notification + Capital Deposit | 3–7 days | D+13 | Jul 30 |
| STEP 4: Corporation Registration | 5–7 days | D+20 | Aug 6 |
| STEP 5: Business Registration | 3–5 days | D+25 | Aug 11 |
| STEP 6: Travel Agency License | 14–30 days | D+55 | Sep 10 |
| STEP 7: Guarantee Insurance | 5–7 days | D+62 | Sep 17 |
| STEP 8: Investor D-8 Visa Support | 30–60 days | D+120 | Oct–Nov |
| Operations Begin | — | — | Late Sep (upon license) |

# STEP 0: Pre-Arrival Preparation (Now – Jul 16)

Duration: Before arrival

1. Sign Shareholder Agreement with investor
   - Equity: Investor 90% / CEO 10%
   - Capital: KRW 100,000,000 (Investor KRW 90,000,000, CEO KRW 10,000,000)
   - CEO: Hee Sung Lee / Director(or Auditor): Investor
   - Include: dividend policy, decision rights, transfer restrictions

2. Investor documents (US)
   - Passport copy (6+ months validity)
   - FBI background check → US Dept. of State Apostille (4–6 weeks; needed for D-8)
   - Source-of-funds documentation (bank statements, tax returns)

3. Engage Korean Certified Legal Administrator (Certified Legal Administrator)
   - Busan-based corporation registration specialist
   - Estimated cost: KRW 500,000–800,000 (incorporation package)

4. Office lease pre-research
   - Small office in Haeundae-gu (KRW 500K–800K/month)
   - Contact real estate agents, compile listing shortlist

5. FDI pre-consultation
   - Call KOTRA Invest KOREA Contact Center (1600-7119)
   - Schedule visit to foreign exchange bank corporate branch

# STEP 1: Office Lease (Jul 17–20, 1–3 days)

Duration: 1–3 days

1. Arrival (Jul 17): Incheon Airport → Busan via KTX (approx. 2h40m)

2. Property visits (Jul 18): 2–3 shortlisted offices in Haeundae-gu
   - Requirements: physical office (no virtual/coworking), Haeundae-gu jurisdiction, formal lease with fixed date stamp
   - Expected deposit: KRW 5M–10M / Monthly rent: KRW 500K–800K

3. Lease signing (Jul 19–20)

[CHECK] Lease agreement copy, Fixed Date Stamp, Office floor plan

# STEP 2: Articles of Incorporation + Notarization (Jul 21–23, 2–3 days)

Duration: 2–3 days

1. Draft Articles (Certified Legal Administrator or startbiz.go.kr)
   - Company: Resonate Club Inc. (Resonate Club Inc.)
   - Purpose: Domestic & International Travel Agency, travel consulting
   - Office: Haeundae-gu, Busan
   - Capital: KRW 100,000,000 (2,000 common shares, KRW 50,000/share)
   - Founders: Hee Sung Lee + [Investor Name]
   - Officers: 1 Representative Director, 1 Director (or Auditor)

2. Notarization: Notary office near Busan District Court Eastern Branch (cost ~KRW 100K–150K)

[CHECK] Notarized Articles, Founder seal certificates

# STEP 3: FDI Notification + Capital Deposit (Jul 24–30, 3–7 days)

Duration: 3–7 days

⚠️ CRITICAL: FDI notification MUST precede capital transfer. Reversing the order triggers penalties and loss of tax benefits.

1. File Foreign Investment Notification (Jul 24–25)
   - At: KOTRA Invest KOREA or foreign exchange bank headquarters
   - Submit: FDI notification form, investor passport, proof of address, business plan, notarized Articles
   - Processing: typically 1–2 days

2. Open capital deposit account (Jul 25–26): Foreign-investment dedicated account at KEB Hana or KB Kookmin Bank

3. Transfer capital (Jul 27–28)
   - Investor: KRW 90,000,000
   - CEO: KRW 10,000,000
   - Bank issues Share Subscription Deposit Certificate

4. FDI Enterprise Registration (Jul 29–30): KOTRA/bank issues FDI certificate

[CHECK] FDI Enterprise Registration Certificate, Share Subscription Deposit Certificate

# STEP 4: Corporation Registration (Jul 31 – Aug 6, 5–7 days)

Duration: 5–7 days

1. Prepare registration application (Jul 31 – Aug 1)
   - Recommend delegating to Certified Legal Administrator (package KRW 500K–800K)
   - Required: notarized Articles, founder seal certificates + resident registration, deposit certificate, CEO acceptance letter, director acceptance letter, application + registration tax

2. File at court (Aug 1–3): Busan District Court Eastern Branch registry or iros.go.kr electronic filing

3. Registration complete (by Aug 6): Corporate Registry Extract, corporate seal card, corporate bank account

[CHECK] Corporate Registry Extract, Corporate Seal Card, Corporate Bank Account

# STEP 5: Business Registration (Aug 7–11, 3–5 days)

Duration: 3–5 days

1. Submit application (Aug 7–8): Haeundae Tax Office or hometax.go.kr online
   - Required: Corporate Registry Extract, lease agreement, Articles, corporate seal certificate, CEO ID

2. Receive Business Registration Certificate (by Aug 11)
   - Business type: Travel Agency (Tourism Promotion Act) / General Taxpayer

[CHECK] Business Registration Certificate

# STEP 6: Travel Agency License (Aug 12 – Sep 10, 14–30 days)

Duration: 2–4 weeks (Haeundae-gu Office + Korea Tourism Organization review)

⚠️ Longest lead time. Document omissions = rejection + another 2–4 weeks.

1. Prepare submission package (Aug 12–14)
   - Tourism Promotion Act Enforcement Rules Art. 9: application form, business plan, Corporate Registry Extract, Business Registration Certificate, lease, capital proof, guarantee insurance certificate, tour escort qualification, fee KRW 50K

2. Submit to Haeundae-gu Office (Aug 14–18): Tourism/Culture & Tourism Division

3. Review period (2–4 weeks): 1st review by district office → technical review by KTO if needed

4. License issued (by Sep 10)

[CHECK] Domestic & International Travel Agency License

# STEP 7: Guarantee Insurance (Aug 12 – Sep 17, parallel with STEP 6)

Duration: SGI review 5–7 days (parallel with STEP 6)

Domestic & International Travel Agency + Planned Travel bond: KRW 230,000,000 total
  → Base bond: KRW 30,000,000
  → Planned Travel surcharge: KRW 200,000,000 (Tourism Act Enforcement Rules Schedule 3)

Legal basis: 'A travel agency operator conducting planned travel shall, in addition to maintaining the guarantee insurance for their license type, additionally subscribe to guarantee insurance for planned travel.'

1. SGI consultation (Aug 12): Busan branch, Yeonje-gu
   - Required: Corporate Registry Extract, Business Registration Certificate, business plan, financial statements, CEO credit consent

2. Insurance application (Aug 14–15)
   - Option A: Full surety bond (zero deposit, annual premium 0.5–1.5%)
     → KRW 230M × 1% = ~KRW 2.3M/year (~KRW 192,000/month)
   - Option B: Partial deposit + surety (if full approval difficult)
     → Example: KRW 50M deposit + KRW 180M surety bond

3. Bond certificates issued (Aug 19–22)

4. Liability insurance: separate mandatory policy (~KRW 35,000/month)

[CHECK] 2 Guarantee Insurance Certificates (base + planned travel), Liability Insurance Certificate

# STEP 8: Investor D-8 Visa Support + Follow-up (Sep onward)

Duration: 30–60 days

Corporation can operate from September. Investor D-8 visa is a separate parallel process.

1. Send required documents to investor: FDI certificate, Corp. Registry Extract (English), Business Registration (English), Shareholder Registry, Articles, Business Plan (English), Office lease

2. Investor applies for D-8-1 visa at Korean Embassy/Consulate in US (5–10 business days)

3. Investor enters Korea → Alien Registration Card (ARC) (within 90 days)

4. Additional registrations: Korea Tourism Association membership, Tour Escort registration, Traveler's Insurance product

D-8 Visa validity: 2–3 years initially, renewable up to 5 years
Permanent Residency (F-5) path: KRW 300M (~$200K) investment OR 2+ full-time Korean employees

# Comprehensive Checklist

| # | Condition | Owner | Deadline |
| --- | --- | --- | --- |
| 1 | Shareholder agreement signed | CEO+Investor | Jul 10 |
| 2 | FBI background check Apostille complete | Investor | Jul 10 |
| 3 | Office lease signed + fixed date stamp | CEO | Jul 20 |
| 4 | Articles notarized | CEO | Jul 23 |
| 5 | FDI notification filed | CEO (with investor POA) | Jul 25 |
| 6 | Capital KRW 100,000,000 fully deposited | Investor+CEO | Jul 28 |
| 7 | FDI Enterprise Registration Certificate received | CEO | Jul 30 |
| 8 | Corporation registration complete | CEO+Certified Legal Administrator | Aug 6 |
| 9 | Business Registration Certificate received | CEO | Aug 11 |
| 10 | Guarantee Insurance bonds issued (KRW 230,000,000) | CEO | Aug 22 |
| 11 | Liability insurance policy active | CEO | Aug 22 |
| 12 | Travel Agency License received | CEO | Sep 10 |
| 13 | D-8 visa application package sent to investor | CEO | Sep 15 |
| 14 | Operations commence | CEO | Late Sep |

---
This document is based on information available as of June 2026. Consult a Korean Certified Legal Administrator and Certified Tax Accountant before proceeding.